## Project Planner
Project Gantt Chart
| Plan Duration |  | Actual Start |  | % Complete |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| ACTIVITY & TASKS | PLAN START (WEEK) | PLAN DURATION (WEEK) | ACTUAL START (WEEK) | ACTUAL DURATION (WEEK) | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Business Understanding | Communicate with client | 1 | 14 | 1 | 14 | 100%
| Access to platform | 1 | 1 | 1 | 1 | 100%
| Review the platform | 1 | 2 | 1 | 2 | 100%
| Project Proposal | 2 | 2 | 2 | 2 | 100%
| Research on user behavior | 3 | 12 | 3 | 12 | 100%
| Research on Descriptive Analysis | 3 | 4 | 3 | 4 | 100%
Data Understanding | Access to database | 4 | 1 | 4 | 1 | 100%
| Data Understanding | 4 | 2 | 4 | 2 | 100%
Data Preparation | Learn SQL | 4 | 4 | 4 | 4 | 100%
| BigQuery Edit | 4 | 4 | 4 | 4 | 100%
| Data Extraction | 6 | 2 | 6 | 2 | 100%
| Data Tranforming | 6 | 2 | 6 | 2 | 100%
Modelling | Build the Dashboard | 8 | 2 | 10 | 2 | 100%
| Design the Dashboard | 8 | 2 | 10 | 2 | 100%
| Updata the Dashboard | 10 | 1 | 11 | 2 | 100%
| Result Analysis | 10 | 2 | 11 | 2 | 100%
Evaluation | Review the Dashboard | 10 | 1 | 11 | 1 | 100%
| Prepare for Presentation | 12 | 2 | 13 | 2 | 50%
| Industry Report | 12 | 3 | 13 | 2 | 50%