## Sheet1
Week | Date | Work Hour | Activity | Outcome
W1 | Aug.27- Sep.02 | 30 | 1. Contact with Tracy and get the access to data. 2. Attend the professional development workshop with ABSL 3. Bi-weekly meeting with Michael 4. Project review with Tracy | 1. Familiar with the organization and data, reviewed the Glory League Platform. 2. Visit the office, meet the whole team and review 2018 season, be familiar with the organization and get some ideas 3. Reviewed the project process and prepare for the project proposal 4. Share our ideas with Tracy and plan to get raw data next week and submit the project proposal next week
W2 | Sep.03- Sep.09 | 30 | 1. Have meeting with Glory League 2. Present our proposal to Glory League team 3. Read the project related papers 4. Do the written work on project proposal | 1. Familiar with Glory League Platform and the process of generating of raw date 2. Reviewed the project process 3. Share our ideas with Glory League team and will get the access of raw data
W3 | Sep.10- Sep.16 | 20 | 1. Read the project related papers 2. Do the written work on project proposal 3. Sign the NDA(NON-DISCLOSURE AGREEMENT) | 1. Get access to database, familiar with Glory League Platform and the database 2. Try to extract the data from Google Cloud Platform 3. Almost finish the project proposal
W4 | Sep.17- Sep.23 | 20 | 1. Review the Literature 2. learn SQL 3. work on the raw data and get clear on the relation between different tables | 1. define the objective of this project 2. revise the project proposal 3. complete part of course about SQL on Udacity
W5 | Sep.24- Sep.30 | 20 | 1. Research on User Behavior Analysis 2. learn SQL 3. work on the raw data and get clear on the relation between different tables | 1. revise the project proposal 2. complete part of course about SQL on Udacity
W6 | Oct.01- Oct.07 | 20 | 1. Research on Descriptive Analysis 2. learn SQL 3. try to write the query on Google BigQuery flatform | 1. complete part of course about SQL on Udacity 2. run BigQuery successfully and get new table contains information of ABSL's users
W7 | Oct.08- Oct.14 | 20 | 1. try to do the primary analysis on the raw data 2. review the Literature about user behavior 3. get clear on the relation between the differnet tables | 1. limit the project data to mixpanel table and only focus on the user belong to ABSL with club ID 25
W8 | Oct.15- Oct.21 | 20 | 1. primary analysis on the mix-panel dataset 2. work on Tableau 3. communicate with GloryLeague on the dataset permission 4. meet ABSL and GloryLeayge team to review the process of the project 5. work on the JSON-encoded data | 1. get the permission of create new table from GloryLeague 2. get the solution to split the eventdata 3. get the primary analysis graphs from Google DataStudio 4. attend Sky City Breakers game at Spark Arena
W9 | Oct.22- Oct.28 | 20 | 1. design Tableau Dashboard 2. result analysis | 1. resolve the JSON-encoded data problem 2.design the dashboard and generate the graphs of timestamp and operation system preference
W10 | Oct.29- Nov.4 | 20 | 1. design Tableau Dashboard 2. result analysis | 1. generate the graphs of browser preference and get panelevent statistical analysis result 2. generate the map show the region of users
W11 | Nov.5- Nov.11 | 20 | 1. review the dashboard and improve it 2. result analysis 3. prepare for presentation 4. meet supervisor to review the project process 5. communicate with client about the project process | 1. improve the design of Tableau Dashboard 2. improve the data structure 3. recommendation on the analysis
W12 | Nov.12- Nov.18 | 20 | 1. review the dashboard and improve it 2. result analysis 3. prepare for presentation | 1. improve the design of Tableau Dashboard 2. improve the data structure 3. recommendation on the analysis
W13 | Nov.19- Nov.25 | 20 | 1. Prepare for Presentation 2.improve the dashboard 3. contact with client about the data analysis results | 1. ready for Presentation 2. get feedback from client about the data analysis results
W14 | Nov.26- Dec.02 | 20 | write Project Report | Project Report
| Total Hours: | 300